Post Implementation Review: Sentiment-Aware Trading Dashboard for Deep Claypot Dashboard Financial, Inc.

Ernest K. Antwi
Western Governors University

Abstract

Deep Claypot Dashboard Financial, Inc. faced a critical operational challenge: an over-reliance on lagging technical indicators that contributed to delayed execution and portfolio erosion, as evidenced by Q4 2025 trading logs showing a 15% execution delay and 5--10% loss in portfolio value. This weakness directly affected three stakeholder groups: five traders experienced decision fatigue due to fragmented data sources, management faced projected 5% client churn and stalled asset growth at $50 million, and the two-person IT department struggled with maintenance burdens and compliance risks. To address these issues, we designed and implemented the Sentiment-Aware Trading Dashboard, a custom Python/Streamlit application that combines real-time equity pricing from the EODHD API with NLP-driven sentiment analysis from VADER, overlaying sentiment metrics directly onto price charts. For traders, the dashboard consolidated multiple feeds into a single intuitive interface; for management, it created a path to reduce churn and restart asset growth; for IT, its modular architecture simplified maintenance and supported FINRA-aligned data handling. The project was executed from January 18 to March 1, 2026, across three structured phases—Planning and Design Development, and Testing and Deployment—and concluded with a live application deployed to all five traders and a full source code handoff to the company. Evaluation included TC-02, which used a 50-headline development validation set, and a summative assessment using a separate 200-headline held-out set to confirm sentiment performance. Overall, this project delivered sustained value beyond remedying a technical deficit, positioning the firm for competitive advantage in sentiment-driven markets.

Keywords: sentiment-aware trading dashboard, Python Streamlit application, EODHD API, market sentiment analysis, stakeholder-centric design, financial data integration, agile project management, post-implementation review

Table of Contents

Abstract…………………………………………………………………………………..2
Quality Assurance………………………………………………………………………..4

Formative Evaluation and QA Metrics……………………………….………….4

Testing Methodology…………………………………………………………….5

Test Cases……………………………………………….……………………….5

Acceptance Criteria……………………………………….…………………...6-7

Project Review…………………………………………………………………………..7

Assumptions……………………………………………………………………..7

Project Phases…………………………………………………………………...7

Timeline Deviations……………………………………………………………10

Project Dependencies…………………………………………………………..10

Resource Requirements……………………………………………………..10-11

Implementation Project Milestones…………………………………………….12

Project Deliverables…………………………………………………………12-13

Documentation Deliverables………………………………………………...13-15

Formative Evaluation Results and Revisions………………………………………..18-19
Summative Evaluation Plan and Results………………………………………………..19
Stakeholder Communication Plan and Reports……………………………………...19-20
Ongoing Support and Maintenance……………………………………………………...21

Resources for Post Implementation Support…………………………………….21

Short-Term and Long-Term Maintenance Plan…………………….....………...22

Post Implementation Project Summary…………………………………………...….…22

Documentation Deliverables……………………………………………………22

Success Criteria for Each Project Outcome…………………………………22-23

Justification of Proposed versus Actual Project Outcomes…………………….23

Lessons Learned………………………………………………………………..24

References…………………………………………………………………………..25-26
Tables…………………………………………………………………………………..27

Post Implementation Report: Sentiment-Aware Trading Dashboard for Deep Claypot Dashboard Financial, Inc

The Sentiment-Aware Trading Dashboard project for Deep Claypot Dashboard Financial, Inc. commenced on January 18, 2026, and concluded successfully on March 1, 2026. This report provides a comprehensive review of the completed project. As detailed in the approved proposal, the firm faced a critical business problem: an over-reliance on lagging technical indicators and fragmented data sources, resulting in delayed decision-making and false trading signals. The approved solution was a custom Python/Streamlit web application that integrates real-time pricing data from the EODHD API with NLP-driven sentiment analysis. The project was implemented using an agile-hybrid methodology across six weeks. Key outcomes included a 72% correlation between sentiment scores and price movements, 100% user adoption among the five traders, and full deployment of the dashboard, which now serves as a central tool for daily trading operations. This report details the quality assurance processes, project execution, stakeholder communication, and ongoing support plan, demonstrating that the project met all objectives and delivered significant value to the firm.

Quality Assurance

We established a rigorous quality assurance framework grounded in the PMBOK Guide’s Manage Quality and Control Quality principles, as described by the Project Management Institute (2021). Our approach was systematic. We defined, tracked, and evaluated specific metrics throughout the project lifecycle to ensure the final deliverable met the defined acceptance criteria and solved the identified business problem. This framework ensured that data from the project, such as sprint burndown rates and user feedback, was used to track progress and support evidence-based decision-making.

Formative Evaluation and QA Metrics

We adopted a formative evaluation approach to monitor project health and make course corrections during implementation. Grounded in the PMBOK Guide's Manage Quality principles, our QA metrics were collected daily, reviewed bi-weekly, and used to drive evidence-based decision-making throughout the project lifecycle (Project Management Institute, 2021). The specific metrics we tracked included:

- Sprint Burndown Rate: Measured remaining story points versus time to ensure each sprint progressed as planned.

- Code Coverage: Pytest-cov verified unit test coverage at 87%, meeting the 80% target.

- Sentiment Accuracy: Measured headline-level classification accuracy against a manually labeled test set (Positive/Negative/Neutral), with a development target of 65 percent or higher.

- User Story Completion Velocity: Tracked the number of user stories completed per sprint against the planned number to gauge team throughput.

Testing Methodology

Using an agile-hybrid approach, we integrated testing throughout development, including unit testing (pytest), integration testing (API connections), system testing (end-to-end data-to-visualization), and formal User acceptance testing (UAT) (February 22–23). We performed integration testing on all API connections, including the EODHD historical, screener, and news APIs, to validate data flow and error handling and to ensure our approach aligned with standard practices for financial data applications (Reddy, 2025; Adithyan, 2025). System testing validated end-to-end functionality, from data ingestion to User Interface (UI) rendering. UAT was conducted on February 22-23. All five traders participated in structured scenarios. They reviewed the dashboard and signed off on its functionality.

Test Cases

We developed a comprehensive suite of test cases that covered all core functionalities. TC-01 verified real-time data loading for the six pre-selected portfolio stocks (NVDA.US, LMT.US, ASML.US, CCO.US, GLD.US, MU.US). It passed with an average load time of 2.3 seconds, meeting the <3-second benchmark. TC-02 validated sentiment classification performance on a labeled test set of 50 financial headlines. The model achieved 78% accuracy, exceeding the 65 percent or higher target. TC-03 tested the alert functionality for a "bullish crossover only if sentiment > 0.5" rule; It triggered correctly for simulated data. TC-04 confirmed successful user login and navigation for all five trader accounts. One minor clarification regarding alert configuration was documented in the user manual and resolved.

Table 5 summarizes the results of the four critical test cases executed during Testing and Deployment.

Rigorous testing was fundamental to our quality assurance framework. During the Testing and Deployment phase, we executed a comprehensive test suite to validate all core functionalities against predefined acceptance criteria. Table 5 summarizes the results of four critical test cases covering real-time data loading, sentiment accuracy, alert triggering, and user access. All test cases passed successfully, with TC-02 exceeding the target accuracy threshold (78% actual vs. 65% expected) and TC-01 meeting the sub-three-second performance benchmark. These results provided quantitative evidence that the dashboard was ready for formal user acceptance testing and final deployment.

Table 5: Test Case Summary

| Test Case ID | Description | Expected Result | Actual Result | Status |
| --- | --- | --- | --- | --- |
| TC-01 | Real-time data load for 6 portfolio stocks (NVDA.US, LMT.US, ASML.US, CCO.US, GLD.US, MU.US) | Load time ≤ 3 seconds | Average load time: 2.3 seconds | Pass |
| TC-02 | Sentiment accuracy on 50 financial headlines | Accuracy ≥ 65% | Accuracy 78% | Pass |
| TC-03 | Alert trigger for bullish crossover with sentiment ≥ 0.5 | Alert generated | Alert generated correctly | Pass |
| TC-04 | User login and navigation for 5 trader accounts | Successful login and full access | Successful for all 5 accounts | Pass |

Acceptance Criteria

Our acceptance criteria were defined at project initiation. They were informed by FINRA-aligned data-handling expectations and the ISO/IEC 25010 software quality model, and were translated into measurable thresholds (e.g., such as 99% uptime or higher and encrypted transport with audit logging) (ISO/IEC 25010, 2018). The final evaluation assessed the dashboard against these benchmarks. Uptime was measured via automated health checks every 5 minutes over the 72-hour period, with failures logged to the audit log. UAT concluded with formal sign-off from all five traders on February 27, and the sponsor (CEO) formally accepted the project on March 1.

Project Review

The project commenced on January 18, 2026, spanned six weeks, and concluded on March 1, 2026. After completion, we conducted a critical review of all phases to evaluate what went well and what required correction. Several key assumptions were made at project initiation, including stable API access and positive trader feedback. To absorb the schedule variance, 10% of the final-week's documentation effort was reallocated.

Assumptions

We made several key assumptions at project initiation. Our assumption of stable API access was challenged when, on January 25, we hit rate limits on the free tier of a news API during peak testing. We resolved this by implementing the planned Redis caching layer to buffer requests and validated stable access using a secure EODHD API key stored in environment variables outside the codebase. Furthermore, our shift to the primary EODHD API token proved resilient, and the data structures returned by the EODHD endpoints for historical, screener, and news data were consistent with the tutorials used during planning (Gonzalez, 2026; Adithyan, 2025). The expectation that the course instructor would serve as a proxy stakeholder for academic requirements was validated; feedback was timely and supported progression through milestones. Our assumption of positive trader feedback was also confirmed; all UI refinements requested during UAT remained within the defined scope and were implemented during Sprint 3. The assumption regarding the availability of the Python ecosystem proved accurate, as all installed libraries functioned without compatibility issues, a reliability we expected given that the combination of Streamlit and financial data libraries is well established in the developer community (Alphasecio, 2026).

Project Phases

The project was structured into three distinct phases, executed as follows:

- Phase 1: Planning and Design (January 18 – January 31, 2026): This phase succeeded admirably. This phase was executed from January 18 – January 31, 2026. Stakeholder workshops on January 18-20 documented user stories using the MoSCoW method (Yalciner, 2023). A key design decision was to adopt a modular architecture inspired by best practices for financial dashboards, separating data fetching, analysis, and visualization logic (Reddy, 2025). Refinements were made, and final approval was obtained on January 26. Architectural design from January 25-29 produced system diagrams and API specifications. The phase concluded on January 31 with 100% stakeholder sign-off on the design (Milestone 1). No significant issues were encountered.

- Phase 2: Development (February 1 – February 21, 2026): This phase progressed through three one-week sprints. Sprint 1 (February 1–7) established the application foundation and integrated the EODHD API for historical and screener data. The foundational knowledge of combining Streamlit with a financial data library, as demonstrated in community projects like the streamlit-yfinance GitHub repository (Alphasecio, 2026), was instrumental in establishing our initial project structure. We successfully integrated the EODHD API for historical and screener data, following the patterns outlined in portfolio optimization tutorials (Adithyan, 2025). Basic charting was completed, and we delivered an internal prototype (demo) on February 7. In this report, 'prototype demo' refers to a stakeholder walkthrough of a working build, while 'MVP build (M2)' refers to the formally completed feature set required for UAT. The initial sentiment model based solely on TextBlob achieved only 55% accuracy on financial headlines, falling short of our 65% benchmark, so we adapted by integrating the VADER library, specifically the FinVADER variant tuned for financial lexicons (Geetha, 2023; PetrKorab, 2023), which resolved the accuracy issue within the sprint buffer. This resolved the accuracy issue within the sprint buffer. Sprint 3 (February 15-21) delivered the final VADER implementation, UI refinements based on formative feedback, and performance optimization. The full sentiment integration and portfolio calculation features were achieved on February 21 (Milestone 3).

- Phase 3: Testing and Deployment (February 22 – March 1, 2026): Testing from February 22-25 included the 72-hour stress test and security audit, followed by documentation compilation and deployment preparation on February 26-27 to configure the Streamlit Community Cloud environment, and this phase executed smoothly overall. On March 1, the dashboard was published to the live URL, and handover meetings were conducted, culminating in a successful launch (Milestone 4).

### Table 4: Project Timeline Gantt (Actual vs. Planned)

Table 4 presents the actual start and end dates recorded during project execution, confirming that all phases and milestones were completed as scheduled. Adherence to the approved schedule was a key success metric for this project. Table 4 provides a side-by-side comparison of the planned and actual timelines for all three project phases and four major milestones, confirming that the project remained on schedule despite minor variances. The data confirms that the project remained on track and launched successfully on April 11, 2026, as scheduled, despite a minor two-day deviation during Sprint 2 to integrate the VADER sentiment library—a necessary course correction identified through formative evaluation. This variance was absorbed by reallocating documentation effort from the final week, demonstrating the effectiveness of our built-in schedule buffers.

Table 4: Project Timeline Gantt (Actual vs. Planned)

| Phase / Milestone | Planned Start | Planned End | Actual Start | Actual End | Variance |
| --- | --- | --- | --- | --- | --- |
| Planning & Design | 1/18/2026 | 1/31/2026 | 1/18/2026 | 1/31/2026 | 0 days |
| Development | 2/1/2026 | 2/21/2026 | 2/1/2026 | 2/21/2026 | 0 days |
| Sprint 2 – VADER integration & refactor | 2/8/2026 | 2/14/2026 | 2/8/2026 | 2/16/2026 | +2 days |
| Testing & Deployment | 2/22/2026 | 3/1/2026 | 2/22/2026 | 3/1/2026 | 0 days |
| M1 – Design approval | — | 1/31/2026 | — | 1/31/2026 | 0 days |
| Prototype demo (internal, not a formal milestone) | — | — | 2/7/2026 | 2/7/2026 | N/A |
| M2 – MVP build (formal completion) | — | 2/14/2026 | — | 2/14/2026 | 0 days |
| M3 – Full sentiment integration | — | 2/21/2026 | — | 2/21/2026 | 0 days |
| M4 – Launch | — | 3/1/2026 | — | 3/1/2026 | 0 days |

Timeline Deviations

One minor deviation in the timeline occurred during the Development. The unplanned VADER integration and subsequent refactoring regression added 2 days to Sprint 2 and delayed the planned documentation start after MVP completion (M2) on February 14. We reallocated 10% of the final week's documentation effort to absorb the variance, while maintaining the final project launch date of March 1. This absorbed the deviation. The final project launch date of March 1 was maintained.

Project Dependencies

Two critical dependencies were identified in the project plan. First, full, authenticated API access (EODHD) was required before Phase 2 could begin. This dependency was secured by January 31; all necessary API keys were obtained and tested. Second, the project depended on receiving written vendor quotes from Dell Technologies by February 1 to finalize the infrastructure proposal. We received these quotes via email from our Dell sales representative on January 31. Both dependencies were managed and tracked in the risk register. Neither impeded progress.

Resource Requirements

Resources were allocated as planned, with a slight variance: the junior developer logged 118 of the planned 120 hours, expending 5,310 of the 5,400 labor budget. The rate of $45.00/hr was benchmarked against and is consistent with BLS data (Bureau of Labor Statistics, 2025). The $10,000 hardware budget was fully allocated to the five Dell Precision 5690 workstations, as per the finalized proposal. Open-source software costs remained at zero. The decision to use a contract developer, rather than a full-time hire, was validated; it delivered a specialized outcome for a fraction of the annual cost of a full-time employee (Fu, 2025). Resource utilization was tracked and reported weekly using an Excel dashboard, with no budget overruns.

Table 3: Resource Allocation Gantt

To maximize developer productivity and minimize context-switching penalties, we implemented a sequential resource allocation strategy. Research on task-switching costs (Weinschenk, 2026) informed our decision to dedicate focused time blocks to specific work streams rather than multitasking across multiple deliverables. Table 3 illustrates how we allocated the junior developer's 120 total hours across the six-week project. During Weeks 1-2, 80% of effort was dedicated to dashboard research and design while concurrently developing hardware specifications. Weeks 3-5 were a 100% intensive development sprint focused solely on coding. The final week shifted to a 70/30 split to complete documentation and finalize the infrastructure proposal.

Table 3: Resource Allocation Gantt

| Week | Dates | Dashboard Dev (% of hours) | Dell Proposal (% of hours) | Total Hours (*) |
| --- | --- | --- | --- | --- |
| 1–2 | Mar 1 – Mar 14 | 80% | 20% | 40 |
| 3–5 | Mar 15 – Apr 4 | 100% | 0% | 60 |
| 6 | Apr 5 – Apr 11 | 70% | 30% | 20 |
| Total |  |  |  | 120 |

Note: Approximate total hours across the six-week project

Implementation Project Milestones

All four key milestones were achieved on schedule.

- M1: Design Approval was finalized on January 31, 2026.

- M2: MVP Build was completed and accepted internally on February 14, 2026 (following the February 7 prototype(demo)).

- M3: Full Sentiment Integration was delivered on February 21, 2026.

- M4: Project Launch occurred on March 1, 2026.

Project Deliverables

The project produced a complete, integrated solution for the company. The primary software deliverable, the live Sentiment-Aware Trading Dashboard, was deployed to a shared company URL on March 1. This fully functional Streamlit application features interactive dashboards with real-time stock visualizations (candlestick charts with 20, 50, and 200-day moving averages) and color-coded sentiment overlays, ready for the trading team's daily use. The dashboard implements the strategic portfolio allocation defined in the code for six key tickers: (NVDA.US, LMT.US, ASML.US, CCO.US, GLD.US, and MU.US). The application's architecture, which separates data fetching, analysis, and visualization into distinct modules, aligns with the structure of successful financial dashboards documented in recent literature (Reddy, 2025; Adithyan, 2025). This approach mirrors the design of systems like TradeForecast, which similarly leverages Streamlit and the yfinance library to create accessible stock analysis tools (Agrawal, 2025). It separates concerns into distinct modules:

- Data Fetching (EODHDDataFetcher class): Handles all interactions with the EODHD API for historical prices, screener data (fundamentals), and news.

- Sentiment Analysis (SentimentAnalyzer class): A singleton class manages the VADER model and processes news headlines.

- Charting (ChartBuilder class): Encapsulates all Plotly chart generation logic, including the portfolio pie chart, the detailed multi-panel price chart with technical indicators (moving averages, Bollinger Bands), and the sentiment gauge.

- Main Application (main() function): Orchestrates the UI flow, user interaction, and calls to the other modules.

The repository was transferred to the company, with an MIT license included to support internal modification and reuse. The Dell infrastructure proposal was delivered as a finalized PDF document. This includes detailed specifications and pricing for five Dell Precision 5690 workstations at $2,000 each, forming a turnkey ecosystem that bridges software innovation with tangible hardware support.

Documentation Deliverables

Several key artifacts were created to document the project and provide evidence of implementation.

Artifact 1: Final Dashboard Screenshot. Figure 1 displays the live Sentiment-Aware Trading Dashboard as deployed on April 11, 2026. The Configuration Panel confirms the primary data source as the EODHD API and selects a 5-year historical time horizon. The Portfolio Metrics Row shows a total portfolio value of $7,066,940 across six active positions, with an average daily change of 0.43%. The Strategic Allocation Table visualizes the target weights for each holding, ranging from 10-20% across Technology, Aerospace & Defense, Semiconductors, Media & Advertising, and gold sectors. The Live Holdings Table provides real-time pricing data, daily percentage changes, trading volume, and 52-week high/low ranges for each ticker. This consolidated view directly addresses the trader stakeholder group's need to reduce decision fatigue by eliminating fragmented data sources.

The live dashboard displays real-time data for all six strategic holdings. As captured in the deployment screenshot on March 1, 2026, the dashboard displayed NVDA.US at $191.55 and LMT.US at $660.62 at the time of capture (values vary with market conditions and API refresh intervals). The sentiment analysis integration is demonstrated through the color-coded headlines panel, where recent news for LMT.US is automatically analyzed and labeled as Positive or Negative using the VADER algorithm. The system correctly identified a strategic acquisition headline as Positive and analyst rating news as Negative, validating the sentiment-price correlation at 72% using Pearson's correlation coefficient between daily returns and daily mean sentiment on a held-out dataset of 200 headlines.

Artifact 2: Source Code Module - Data Fetcher. A snippet from claypot_dash2.py (Figure 2) demonstrates the modular EODHDDataFetcher class. Figure 2 presents a code snippet from claypot_dash2.py showing the get_historical_prices method within the EODHDDataFetcher class.

This method encapsulates the core logic for retrieving historical price data from the EODHD API, implementing patterns documented in financial dashboard tutorials (Adithyan, 2025). The method accepts a ticker symbol and a time period, calculates the appropriate date range using _get_period_dates, constructs the API request with the proper authentication parameters, and handles the JSON response. Error handling is implemented through try-except blocks, and the method returns a structured StockData object containing standardized price history, current price, daily change calculations, and 52-week high/low values. This modular design—separating data fetching logic into its own class—was a direct outcome of our design phase and a key factor in simplifying long-term maintenance for the IT department, as changes to data sources can now be isolated to this single class without impacting the UI or analysis modules.

The get_fundamental_data method implements the EODHD Screener API logic documented in Python financial tutorials (Gonzalez, 2026). The method dynamically constructs a JSON filter string targeting a specific ticker symbol, sends a request to the screener endpoint with appropriate authentication parameters, and parses the response to extract fundamental data such as market capitalization. Error handling is implemented using try-except blocks, with warnings logged for failed requests. The method returns a structured dictionary containing the screener results, which are then used to populate the market capitalization field in the Live Holdings Table shown in Figure 1.

This modular design is separating data fetching logic into dedicated methods within its own class—was a direct outcome of our design phase and a key factor in simplifying long-term maintenance for the IT department. Changes to either the historical price endpoint or the screener API can now be isolated to their respective methods without impacting the UI, analysis modules, or each other. This separation of concerns directly addresses the stakeholder requirement for a system that minimizes maintenance burdens while ensuring FINRA compliance through consistent, auditable data handling.

Artifact 3: Test Case Summary. Table 5 (see Tables section) provides a quantitative summary of our testing. It lists key test cases, expected results, and actual outcomes. This table validates the quality assurance process and demonstrates that all core functionalities were thoroughly tested and passed.

Table 2: MSITM Capstone Risk Register

Proactive risk management was embedded throughout the project lifecycle. In accordance with the PMBOK guidelines (Project Management Institute, 2021), we established a comprehensive risk register during the Planning and Design phase to identify, assess, and mitigate potential threats to project success. Table 2 presents the final, updated risk register as of project completion, highlighting how we monitored and controlled the five most critical project vulnerabilities. It details the five critical vulnerabilities we monitored—API instability, sentiment model accuracy, scope creep, user adoption resistance, and deployment security—along with their likelihood, potential consequences, and the specific mitigation strategies we implemented. This register was reviewed bi-weekly at project status meetings to ensure all risks remained within acceptable thresholds.

Table 2: MSITM Capstone Risk Register

| Asset | Threat/Vulnerability | Existing Controls | Likelihood (1-5) | Consequence (1-5) | Level of Risk (L*C) | Risk Priority | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| API Integration | Downtime or rate limiting | Redundant endpoints | 3 | 4 | 12 | High | Local caching, fallback sources (Polygon.io) |
| Sentiment Model Accuracy | Bias in NLP libraries | Hybrid VADER+TextBlob | 2 | 5 | 10 | Medium | User feedback tuning, validation datasets |
| Scope Creep | Unrequested features | MoSCoW prioritization (Yalciner, 2023) | 4 | 3 | 12 | High | Strict scope document, weekly reviews |
| User Adoption | Resistance to the new tool | Intuitive UI design | 3 | 4 | 12 | High | Training sessions, pilot testing |
| Deployment Security | Data breach in Streamlit hosting | Encryption, access controls | 2 | 5 | 10 | Medium | Compliance audits, HTTPS enforcement |

Formative Evaluation Results and Revisions

Formative evaluation identified a critical performance gap in Sprint 2. During the February 11 Sprint 2 review, the TextBlob-only sentiment model achieved 55% accuracy on a financial headline test set, falling short of the 65% benchmark. After reviewing the error patterns and evaluating alternatives, the team selected FinVADER, a VADER variant enhanced with financial lexicons, as the most suitable corrective action (Geetha, 2023; PetrKorab, 2023). The initial FinVADER integration and baseline validation were completed by February 14; Sprint 2 formally closed on February 16 after refactoring and regression testing, which added two buffer days. Post-integration testing confirmed sentiment accuracy improved to 70, resolving the accuracy shortfall risk and restoring sprint viability.

A second, minor revision was made following UAT feedback on February 20. Traders requested that the sentiment score be displayed numerically in addition to the color-coded gauge, and this nice-to-have enhancement was implemented within one day to improve usability without introducing scope creep.

Summative Evaluation Plan and Results

We executed the final summative evaluation as planned. The 72-hour stress test conducted from February 22–25 confirmed 99.2% uptime, surpassing the 99% target, with performance measured via automated health checks every five minutes and all failures logged to the audit log. The final sentiment correlation reached 72% when the hybrid model was run against a larger, held-out dataset of 200 headlines, placing it squarely within the 65-75% target range. The security audit verified full compliance with FINRA guidelines (Agnew et al., 2025), including encrypted data transmission and comprehensive audit trails for all data access. The project met all predefined acceptance criteria. Based on these results and successful UAT, the project was formally accepted by the sponsor on March 1.

Stakeholder Communication Plan and Reports

We implemented the structured communication plan outlined in Task 2. It worked effectively to ensure all stakeholders were involved and informed. Traders received weekly demos and participated in feedback sessions. Their input shaped the UI refinements in Sprint 3, specifically the numerical sentiment display and the layout of the multi-panel chart. Management (CEO, CFO) received executive summaries via email on January 31 (end of Planning phase) and March 2 (post-launch), including the final ROI and KPI recap. The March 2 briefing included a final ROI summary and KPI dashboard, both of which referenced the project’s alignment with Vanguard’s principles of disciplined investing (Vanguard Group, 2023). The IT department participated in joint technical audits on February 22 and 25. They received full technical documentation and access to the source code via the GitHub repository upon project completion.

The final dashboard itself provides tangible evidence that the structured stakeholder communication plan succeeded, and each stakeholder group’s needs are visibly addressed in the live application:

- For Traders: The interface consolidates six data streams into a single view, showing price, volume, technical ranges, and sentiment headlines simultaneously, directly addressing the decision fatigue identified in Q4 2025 trading logs.

- For Management: The $7,066,940-portfolio valuation and 0.43 average daily change provide immediate visibility into the impact of sentiment-aware trading decisions, directly supporting the goal of reversing client churn and restoring asset growth.

- For IT: The clear attribution of "EODHD Historical & News APIs" confirms the modular data architecture implemented during development, simplifying future maintenance and troubleshooting while ensuring FINRA compliance.

This multi-layered approach ensured alignment, facilitated swift final acceptance, and built stakeholder buy-in for the new tool. The evidence is visible in every interaction with the dashboard.

Table 1: Stakeholder Communication Plan

Effective stakeholder engagement was critical to project success. We developed a formal Stakeholder Communication Plan at project initiation to ensure each group's unique needs were addressed through tailored communication channels. Table 1 outlines the three primary stakeholder groups, the specific impacts they experienced from the legacy system, the benefits the new dashboard provides to each group, and the structured communication approach we used throughout the six-week implementation. This plan ensured that traders received weekly hands-on demos, management received monthly high-level briefings, and IT participated in joint technical audits.

Table 1: Stakeholder Communication Plan

| Stakeholder Group | Current Impact | Solution Benefits | Communication Plan |
| --- | --- | --- | --- |
| Traders | Decision lag, false signals, and frustration from fragmented data | Consolidated single-view interface with price, volume, technical ranges, and sentiment headlines simultaneously, reducing decision fatigue and false trading signals | Weekly demos, feedback surveys, and UAT participation |
| Management | Client churn, revenue stagnation, and stalled asset growth at $50M | Real-time portfolio visibility ($7.07M valuation and 0.43% average daily change) supporting KPI tracking and ROI analysis | Monthly executive briefs, KPI dashboards, and final ROI briefing (January 31 and March 2 emails) |
| IT Department | Maintenance overload and compliance risks from fragmented tools | Modular Python architecture with clear EODHD API attribution, simplified troubleshooting, and FINRA-aligned data handling | Technical audits (February 22 and 25), joint workshops, and full documentation handover |

Ongoing Support and Maintenance

An overview of the plan for ongoing support and maintenance of the project deliverables is provided below. This ensures the implemented solution remains optimal.

Resources for Post Implementation Support

Post implementation resources have been allocated. For the first 30 days post-launch (through May 11, 2026), a hyper-care support period is in effect. The developer (Ernest Antwi) and the IT lead have been designated as the primary contacts, with a guaranteed response time of 4 business hours. This support is provided via a dedicated Slack channel and email triage system. For long-term support, 5% of the IT department’s quarterly operational budget, approximately $1,500 per quarter, has been allocated for maintenance. This funding will be drawn from the existing departmental budget and covers potential costs for API upgrades (e.g., moving from EODHD's free tier to a paid tier if usage increases), dependency patches, and minor feature enhancements.

Short-Term and Long-Term Maintenance Plan

With the project successfully completed on March 1, 2026, the following post-implementation support plan establishes ongoing maintenance activities with all dates in the future. A detailed maintenance plan has been developed, and short-term maintenance for March–May 2026 is scheduled to ensure code quality and timely bug resolution. Monthly code reviews are planned by the IT lead to ensure code quality and address any minor bugs. User feedback will be collected via a short survey at the end of each month and reviewed for potential minor patches. The dashboard's modular architecture, separating data fetching, analysis, and UI, is key to this maintainability (Reddy, 2025).

Long-term maintenance is scheduled for the first week of June 2026, September 2026, and December 2026. This ensures all libraries remain current and secure. A major version review (v2.0) is planned for Q1 2027 (January 2027). This review will assess the feasibility of adding new data sources, such as the Reddit API via the praw library (Kokate, 2024), implementing more advanced ML models, such as FinBERT for financial text analysis (Huang et al., 2022), or expanding the tool to support cryptocurrency assets using EODHD's crypto endpoints.

Post Implementation Project Summary

This post-implementation summary recaps the project’s journey and outcomes and provides a basis for reflecting on what should be repeated and improved in future initiatives. The business problem centered on an over-reliance on lagging indicators and fragmented data, which caused significant financial losses. The proposed solution was the Sentiment-Aware Trading Dashboard. It was implemented over six weeks using an agile-hybrid methodology. The final outcomes include a fully functional dashboard, full user adoption, and validated success metrics, demonstrating that sentiment-aware analytics can be integrated rapidly when supported by a modular architecture and disciplined project governance.

Documentation Deliverables

The project was delivered as proposed: the live Streamlit application was transitioned to the company. The complete source code repository and technical documentation were provided to the IT team. The Dell infrastructure proposal was finalized and handed over to management for procurement action.

Success Criteria for Each Project Outcome

All success criteria were met.

- Sentiment-Price Correlation: The 65-75% correlation target was achieved with a final summative result of 72%, validated against a held-out dataset.

- User Adoption: The 75% user adoption goal was not only met but exceeded; post-launch logs from March 2-8 show all five traders (100%) actively logged in and using the dashboard daily.

- False Signal Reduction: A 20% false-signal reduction is projected relative to Q4 2025 baseline logs. This projection will be validated in Q1 2027 using updated trading performance data.

- ROI: ROI is projected at 120%, based on $15,400 total implementation cost (labor: $5,310, hardware: $10,000) and $18,500 annualized benefit from reduced trading delays and churn avoidance.

- Compliance: All regulatory acceptance criteria were met, as confirmed by the security audit.

Justification of Proposed versus Actual Project Outcomes

One deviation from the initial proposal occurred. The initial proposal in Task 2 specified using VADER and TextBlob. The plan called for a TextBlob-only model for the initial build. The actual outcome included a hybrid VADER-TextBlob model, with VADER (FinVADER) becoming the primary analyzer. This change was necessitated by formative evaluation data that showed TextBlob's limitations with financial terminology. It was fully justified. The hybrid model delivered higher sentiment accuracy (72% actual vs. 65% minimum target). This improved the final outcome and better addressed the business need for accurate qualitative context. A second deviation was the shift from the originally proposed library to the EODHD API as the primary data source. This change was driven by EODHD's more comprehensive and stable API for fundamental data (screener) and news, which was essential for building a fully-featured, sentiment-aware dashboard, as inspired by the reviewed tutorials (Gonzalez, 2026; Adithyan, 2025). The budget and timeline impact of both changes were minor and absorbed as detailed in the Timeline Deviations section. All other outcomes matched or exceeded the proposed plan.

Lessons Learned

The key lesson learned was the critical importance of early, rigorous formative evaluation. Discovering TextBlob's limitations in mid-sprint was far less costly than discovering them at project end. This validates our agile-hybrid approach. The structured feedback loops with traders also proved invaluable; their UAT input directly improved the tool's usability and ensured high adoption. A second lesson was the effectiveness of the resource allocation plan. Sequestering developer time to focus on a single workstream, as supported by research on task-switching costs (Weinschenk, 2026), prevented the productivity loss that could have occurred from juggling multiple unrelated tasks. A third lesson was the value of using well-documented technical tutorials for planning. Referencing the work of Reddy (2025) and others during the design phase gave our team a clear architectural blueprint and reduced technical uncertainty. Future projects at Deep Claypot will standardize even more aggressive early prototyping of high-risk technical components. We will implement this protocol. We will apply this lesson by requiring a mandatory "technical spike" in the first sprint of any future project that involves new, unproven libraries or APIs. This will de-risk the development cycle from the outset.

References

Adithyan, N. (2025, December 15). Building a portfolio optimization app with Streamlit and python. InsightBig. https://www.insightbig.com/post/building-a-portfolio-optimization-app-with-streamlit-and-python

Agnew, K., Chiang, C., & Sprecher, C. (2025, August 28). The SEC finalizes rule on cybersecurity disclosures. The CPA Journal. https://www.cpajournal.com/2025/08/27/the-sec-finalizes-rule-on-cybersecurity-disclosures/#:~:text=The%20SEC’s%20new%20cybersecurity%20rules%20require%20that%20public%20companies%20promptly,regarding%20their%20cyber%20governance%20policies.

Agrawal, P. (2025). TradeForecast : Stock Performance and Prediction Web Application, 1–8. https://doi.org/10.2139/ssrn.5198474

Alphasecio. (2026). Alphasecio/Streamlit-yfinance: A Streamlit app for simple financial analysis using yfinance API. GitHub. https://github.com/alphasecio/streamlit-yfinance

Bureau of Labor Statistics. (2025, August 28). Software developers, Quality Assurance Analysts, and Testers. U.S. Bureau of Labor Statistics. https://www.bls.gov/ooh/computer-and-information-technology/software-developers.htm

Fu, J. (2025, June 10). How much to hire a software developer: Freelance vs full-time costs. Arc Employer Blog. https://arc.dev/employer-blog/software-developer-freelance-vs-full-time-costs/

Geetha, L. (2023). Vader: A comprehensive guide to sentiment analysis in python. medium.com. https://medium.com/@rslavanyageetha/vader-a-comprehensive-guide-to-sentiment-analysis-in-python-c4f1868b0d2e

Huang, A. H., Wang, H., & Yang, Y. (2022, September). Finbert: A large language model for extracting information from financial text* - huang - 2023 - contemporary accounting research - wiley online library. Wiley Online Library. https://onlinelibrary.wiley.com/doi/abs/10.1111/1911-3846.12832

International Organization for Standardization. (2018). Systems and software engineering—Systems and software Quality Requirements and Evaluation (SQuaRE)—System and software quality models (ISO/IEC Standard No. 25010:2018). https://www.iso.org/standard/64764.html

Kenton, W., & Jackson, A. (2025). What is the International Organization for Standardization (ISO)?. Investopedia. https://www.investopedia.com/terms/i/international-organization-for-standardization-iso.asp

Kokate, A. (2024, March). Scraping Reddit and Subreddit Data Using Python and Praw : A Beginner’s Guide | by Archana Kokate | Mar, 2024 | medium | medium. Medium. https://medium.com/@archanakkokate/scraping-reddit-data-using-python-and-praw-a-beginners-guide-7047962f5d29

PetrKorab. (2023). Petrkorab/Finvader: Vader sentiment classifier updated with financial lexicons. GitHub. https://github.com/PetrKorab/FinVADER

Project Management Institute. (2021). A guide to the project

management body of knowledge (PMBOK guide) (7th ed.). PMI.

Reddy, K. (2025, February). Building an interactive financial dashboard with Streamlit and plotly: A step-by-step tutorial | by Karthikeya Reddy | Medium. Building an Interactive Financial Dashboard with Streamlitand Plotly: A Step-by-Step Tutorial. https://reddykarthikeya1.medium.com/building-an-interactive-financial-dashboard-with-streamlit-and-plotly-a-step-by-step-tutorial-4b9973b62be5

Vanguard Group. (2023). Vanguard Research Vanguard’s principles for investing success. Vanguard’s Principles  for Investing Success. https://corporate.vanguard.com/content/dam/corp/research/pdf/vanguards_principles_for_investing_success.pdf

Weinschenk, S. (2026). The true cost of multi-tasking. The True Cost of Multi-Tasking. https://www.psychologytoday.com/us/blog/brain-wise/201209/the-true-cost-of-multi-tasking

Yalciner, Y. E. (2023). The Moscow Method: A Comprehensive Guide to Prioritization in Project Management | by Yunus Emre Yalçıner | Medium. medium.com. https://medium.com/@emre.yancizer/the-moscow-method-a-comprehensive-guide-to-prioritization-in-project-management-85f530aa1dcd

Tables

Table 1: Stakeholder Communication Plan (p. 20-21)

Table 2: MSITM Capstone Risk Register (p. 16-18)

Table 3: Resource Allocation Gantt (p. 11)

Table 4: Project Timeline Gantt (Actual vs. Planned) (p. 9-10)

Table 5: Test Case Summary (p. 6)